## Instructions
iTech Exploring Plug and Play Schedule
These templates are a resource for COUNCILS, PARTICIPATING ORGANIZATIONS and UNITS (posts or clubs) to plan your iTech Exploring program. The iTech Exploring “Plug and Play” schedule is designed to jump start your program planning process.
Below is an overview of each tab.
w | Council Schedule: Designed for district/Exploring executives and your volunteer committees from the local council to integrate the iTech Exploring program into current council operations.
w | Organization Schedule: Designed for the business or organization who is starting their own iTech Exploring post (14-20 year olds) or club (6th grade -14 year olds).
w | Unit Schedule: Designed for the Exploring post or club unit committee to plan your iTech Exploring program schedule. Choose the schedule (one or two semesters) that’s right for your needs. Activities in BOLD PRINT are required. Then populate the schedule with your own activities or choose activities from the Exploring Activity Library at www.exploring.org. Fill in meeting dates and site visit locations. Once you have created your unit's schedule, share it with your Explorers and their parents.
A minimum of 15 meetings with the same group of Explorers is required to deliver a quality program with a lasting impact.

## Council Schedule
iTech Roadmap for the Local Council
DONE | ASSIGNED TO | STEP | SCHEDULE FOR COUNCILS | SUPPORT MATERIALS
|  | 1 | Review the iTech Exploring in the Local Council that explains how iTech Exploring can boost your council’s engagement in the community and determine whether your board will support the initiative. | iTech Exploring in the Local Council (coming soon)
|  | 2 | Hire or designate an iTech Exploring Director. | Business Case for hiring an iTech Exploring Director (coming soon); iTech Exploring Director Position Description at exploring.org/itech
|  | 3 | Recruit an iTech Exploring Chair to serve for a two-year term. | Find the iTech Exploring Chair Position Description at exploring.org/itech in the Council Resources box.
|  | 4 | Build your iTech Exploring Committee to support the four functions of Exploring operations: marketing, service, program, and fundraising. | iTech Chair and Committee Member position descriptions at exploring.org/itech.
|  | 5 | Develop market-specific promotional materials. | Find templates and other iTech Exploring collateral in the BSA Brand Center (coming soon).
|  | 6 | Gather and review career interest data for tech-related career interests. | STEM Premier, Exploring Career Interest Survey results, schools' own career interest data
|  | 7 | Recruit hub and site visit partners that align with local student career interest data. | Find the iTech Exploring sales infographic and other iTech Exploring collateral in the BSA Brand Center (coming soon).
|  | 8 | Build list of potential participating organizations that align with local student career interest data. | Exploring Unit Performace Guide and Tracking Sheet found at exploring.org in the Council Resources box.
|  | 9 | Confirm participating organizations with signed MOU's. | iTech Exploring sales PPT and Exploring MOU found at exploring.org/iTech in the resource boxes.
|  | 10 | Innovation Design Challenge Prep: Get familiar with national IDC's. | iTech IDC Prep Activity
|  | 11 | Innovation Design Challenge Prep: Coordinate local IDC showcase or competition. | Council Coordinated iTech IDC Tips (coming soon)
|  | 12 | Establish Service Teams or orient your council's current Commissioner teams to iTech Exploring needs. | Commissioner Service to Exploring FAQ's, Commissioner Service to Exploring PPT, Exploring Service Team Training online module
|  | 13 | Conduct iTech Program Planning mtg + Exploring leader orientation for multiple iTech units in person. | Consider a council-wide Program Planning Meeting with organization-specific breakouts when appropriate.
iTech Roadmap for the Local Council (cont'd)
DONE | ASSIGNED TO | STEP | ROADMAP FOR COUNCILS | SUPPORT MATERIALS
|  | 14 | Schedule site visits with potential partners and/or participating organizations | iTech Sales PPT, iTech Sales Infographic
|  | 15 | Assist with Open Houses | Open House Agenda, open house fliers & other marketing collateral is available online at the BSA Marketing & Membership Hub
|  | 16 | Ongoing unit support from iTech Exploring Service Team | Commissioner Tools at my.scouting. Unit Commissioners, Service Team Members, or higher Commissioner positions can record unit visits in Commissioner Tools for Exploring units.
|  | 17 | Begin developing potential iTech Exploring funding partners | Work with your council's Development Director or other manager.
Download this iTech sales infographic at www.exploring.org/itech from the Council Resources box.

## Organization Schedule
iTech Roadmap for the Participating Organization
DONE | ASSIGNED TO | STEP | ROADMAP FOR ORGANIZATIONS | SUPPORT MATERIALS
|  | 1 | Sign the Memorandum of Understanding with your local Exploring representative. | Exploring MOU
|  | 2 | Review Exploring's New Unit Playbook - phases 2, 3 and 4 - to confirm your understanding of how to get your iTech Exploring program up and running. | New Unit Playbook, Phases 2 - 4
|  | 3 | Select at least 6 adults to serve as the post/club unit committee. | Exploring Guidebook for Leaders, pages 12 - 21, unit committee position descriptions
|  | 4 | Unit committee members should complete online Youth Protection Training (YPT) before attending the Program Planning meeting. | Access Youth Protection Training online at my.scouting.org.
|  | 5 | The entire unit committee attends the All-in-One Program Planning Meeting and signs required applications. Determine which of the 4 Innovation Design Challenge formats your unit will pursue at this meeting. | Your local Exploring representative will lead this planning meeting with the unit committee (typically employees of the organization). iTech Exploring Plug and Play Schedule; iTech IDC Prep Activity
|  | 6 | Unit committee members complete online training modules before the open house. | Review these FAQ's that link to the online training.
|  | 7 | Schedule and prepare for your open house to recruit and register local youth. | Suggested open house agenda, found in the Exploring Guidebook for Leaders - page 125
|  | 8 | Set your meeting schedule and program fees, if applicable. | iTech Exploring Plug and Play Schedule template. Consult with your local Exploring representative regarding program fees.
|  | 9 | Send open house invitations to youth, share on social media, and invite children of your employees. | Your local Exploring representative can provide contact information for youth interested in your industry. Determine the max number of students your facility can serve on a regular basis (suggested minimum of 10).
|  | 10 | Conduct the open house, collect youth applications and program fees if applicable. | Exploring Youth Application
|  | 11 | Follow your post or club's schedule of meeting activities | iTech Exploring Plug and Play Schedule

## Unit Schedule - Two Semesters
Post/Club No. & Name
Leader Name & Phone
Meeting Place & Time
NOTE: All supporting resources listed in italics are found in Exploring Activity Library at exploring.org.
| Meeting | Date | Meeting Activity | Suggested Youth Leadership Role(s) | Supporting Resources
Semester 1 | September |  | Open House | N/A | Sample Open House Agenda
| Oct. Meeting 1 |  | First Day Logistics & Intro to Innovation | N/A | iTech Leader Guide; Intro to Innovation
| Oct. Meeting 2 |  | SITE VISIT - organized by unit committee | N/A | Consider touring your own place of business
| Oct. Meeting 3 |  | Discuss the concept of project management as it relates to the workplace | N/A | Project Management
| Nov. Meeting 1 |  | Innovation Design Challenge preparation, search and selection | N/A | iTech IDC Prep
| Nov. Meeting 2 |  | SITE VISIT - organized by unit committee | N/A | Consider touring a facility relevant to your selected Innovation Design Challenge
| Nov. Meeting 3 |  | Introduce Explorers to youth leadership roles & host elections | N/A | iTech Youth Leadership Roles
| Dec. Meeting 1 |  |  |  | Exploring Activity Library career and life skills activity OR an activity specific to your organization
Dec. Meeting 2
| Dec. Meeting 3 |  | Holiday Celebration!
| Meeting | Date | Meeting Activity | Suggested Youth Leadership Role(s) | Supporting Resources
Semester 2 | Jan. Meeting 1 |  |  |  | Exploring Activity Library career and life skills activity OR an activity specific to your organization
Jan. Meeting 2
Jan. Meeting 3
Feb. Meeting 1
| Feb. Meeting 2 |  | Plan your unit's budget for the year with Explorers' input | Project Manager, Treasurer | Budget Planning
| Feb. Meeting 3 |  | Innovation Design 1 related to your selected IDC | Research Manager, Project Manager | iTech Innovation Design 1
| Mar. Meeting 1 |  | SITE VISIT - organized by Explorer | Site Visit Coordinator | Coordinating a Site Visit
| Mar. Meeting 2 |  | Innovation Design 2 related to your selected IDC | Project Manager, QA Manager | iTech Innovation Design 2
| Mar. Meeting 3 |  | Innovation Design 3 related to your selected IDC | Design & User Feedback Manager, Project Manager | iTech Innovation Design 3
| Apr. Meeting 1 |  | SITE VISIT - organized by an Explorer | Site Visit Coordinator | Coordinating a Site Visit
| Apr. Meeting 2 |  | Innovation Design 4 related to your selected IDC | Project Manager, Design & User Feedback Manager, QA Manager | iTech Innovation Design 4
| Apr. Meeting 3 |  | Repeat Design 4 as many times as needed to reach your IDC goal | Project Manager, Design & User Feedback Manager, QA Manager | iTech Innovation Design 4
| Apr. Meeting 4 |  | SITE VISIT - organized by an Explorer | Site Visit Coordinator | Coordinating a Site Visit
| May Meeting 1 |  | Repeat Innovation Design 4 as many times as needed to reach your IDC goal | Project Manager, Design & User Feedback Manager, QA Manager | iTech Innovation Design 4
| May Meeting 2 |  | IDC Event Practice | IDC Event Coordinator | Personal Presentations in Professional Settings; Refer back to iTech IDC Prep
| May Meeting 3 |  | IDC Event | IDC Event Coordinator | Refer back to iTech IDC Prep
| May Meeting 4 |  | Reflect on your iTech Exploring and IDC experience | Project Manager, IDC Event Coordinator | iTech Innovation Reflection

## Unit Schedule - One Semester
Post/Club No. & Name
Leader Name & Phone
Meeting Place & Time
NOTE: All supporting resources listed in italics are found in Exploring Activity Library at exploring.org.
Meeting | Date | Meeting Activity | Suggested Youth Leadership Role(s) | Supporting Resources
Meeting 1 |  | Open House | N/A | Sample Open House Agenda
Meeting 2 |  | First Day Logistics & Intro to Innovation | N/A | iTech Leader Guide; Intro to Innovation
Meeting 3 |  | SITE VISIT - organized by unit committee | N/A | Consider touring your own place of business
Meeting 4 |  | Discuss project management as it relates to the workplace | N/A | Project Management
Meeting 5 |  | Innovation Design Challenge search and selection | N/A | iTech IDC Prep
Meeting 6 |  | Introduce Explorers to youth leadership roles & host elections | N/A | iTech Youth Leadership Roles
Meeting 7 |  | SITE VISIT - organized by unit committee | Site Visit Coordinator | Consider touring a facility relevant to your selected Innovation Design Challenge
Meeting 8 |  | Plan your unit's budget for the year with Explorers' input | Project Manager, Treasurer | Budget Planning
Meeting 9 |  | Innovation Design 1 related to your selected IDC | Research Manager, Project Manager | iTech Innovation Design 1
Meeting 10 |  | Innovation Design 2 related to your selected IDC | Project Manager, QA Manager | iTech Innovation Design 2
Meeting 11 |  | Innovation Design 3 related to your selected IDC | Design & User Feedback Manager, Project Manager | iTech Innovation Design 3
Meeting 12 |  | SITE VISIT - organized by an Explorer | Site Visit Coordinator | Coordinating a Site Visit
Meeting 13 |  | Repeat Innovation Design 4 as many times as needed to reach your IDC goal | Project Manager, Design & User Feedback Manager, QA Manager | iTech Innovation Design 4
Meeting 14 |  | IDC Event Practice | IDC Event Coordinator | Personal Presentations in Professional Settings; Refer back to iTech IDC Prep
Meeting 15 |  | IDC Event | IDC Event Coordinator | Refer back to iTech IDC Prep
Meeting 16 |  | Reflect on your iTech Exploring and IDC experience | Project Manager, IDC Event Coordinator | iTech Innovation Reflection